PMT NOTE on Essar Power (March 30, 2026)

Essar Power Limited (EPOL)

1. Strategic Initiatives & Capital Plan (FY 2026-27)

| Initiative | Status | FY27 Target (Rs. Cr) | Funding Source | Net Margin (Rs. Cr) | Reference |
| --- | --- | --- | --- | --- | --- |
| EPC for ERL Renewable Projects (900 MW) | PPAs under discussion with SJVN & NHPC; LoAs issued for all 3 projects | 1,018 (Revenue) | ERL project funding; cost pass-through | 150 | EPOL ABP p.3:4, p.12 |
| SEZ Development at Salaya | Application to Gujarat Govt for license; 60-hectare land subleased from EPGL | 55 (Revenue) | EFEL payment to EPOL as developer | 30 | EPOL ABP p.4, p.12 |
| Brand Merger with AVPL | NCLT Ahmedabad application filed; approval pending | 430 (Revenue) | Post-merger revenue stream (AMNS/Nayara) | — | EPOL ABP p.4, p.12:14 |
| Coal Trading | One consignment executed in FY25-26 | 400 (Revenue) | Coal purchase Rs.396 Cr | 4 | EPOL ABP p.4, p.12 |
| Equity Infusion into ERL | FOCC constraint — equity or internal accruals only | 874 (Equity Inv.) | EGFL equity Rs.550 Cr + EPOL accruals | — | EPOL ABP p.11:12 |
| Equity Infusion into EFEL (Bio Refinery) | Board approved 26% stake; commissioning targeted 2028 | 100 (Equity Inv.) | EPOL internal accruals | — | EPOL ABP p.4, p.12 |
| NCD Repayment to Alpha & Others | Rs.867 Cr NCDs at 20.5% coupon; repayment in Q4 | 867 (Debt repayment) | EPGL OCD redemption Rs.400 Cr + GUVNL receipt Rs.650 Cr | — | EPOL ABP p.11:13, p.15 |
| EPTCL Stage 1 Tariff Arrear | APTEL judgment 11.12.2024; CERC order for 2013-14 passed; 14:19 & 19:24 petitions pending filing by AMNS | 188 | Recovery from CTUIL in 3 tranches | — | EPOL ABP p.8, p.12 |

2. Litigation & Contingent Liabilities

| Case | Amount at Risk (Rs. Cr) | Current Status | Timeline | Reference |
| --- | --- | --- | --- | --- |
| GUVNL : Wrongful Deduction | ~1,992 | GERC ordered Rs.654 Cr (simple interest); EPOL seeking compound interest (Rs.1,733 Cr) at APTEL. Execution order set off against wrongful allocation claim. EPOL challenging set-off at APTEL. | FY 26-27 | EPOL ABP p.8:9 |
| Income Tax Demand (AY 2023-24) | 350 | AO disallowed Rs.361 Cr as unexplained cash credits u/s 68. Appeal filed before CIT(A) on 23-Apr-2025; stay application pending, no coercive action. | FY 26-27 | EPOL ABP p.16 |
| NCLT : EPJL Liquidation IAs | 346 | Multiple IAs: Rs.317 Cr u/s 66 IBC (contribution claim); Rs.28 Cr u/s 43-44 IBC (preferential transactions); DK Khosla application to invoke EGFL/EPOL guarantees. | FY 27-28 | EPOL ABP p.17 |
| BG Release (BTPPL/PGCIL) | 36 | APTEL directed BG return; CTUIL challenged before Supreme Court. SC ordered status quo on 26.09.2025; stay application yet to be heard. | FY 26-27 | EPOL ABP p.16 |
| Chakla Coal Mine Compensation | 50 | Compensation of Rs.50.22 Cr paid to EPOL in 2022. Orissa Alloy (purchaser of EPJL) filed writ in Delhi HC claiming compensation belongs to EPJL. | FY 26-27 | EPOL ABP p.20 |
| GSPL Ship-or-Pay Charges | 27 | SC struck down PNGRB Guidelines (19.03.2025). GSPL issued demand letters for Rs.14.66 Cr. EPOL contends claims barred by limitation. GERC petition pending. | FY 27-28 | EPOL ABP p.18:19 |

3. Standalone Financials (Rs. Cr)

Standalone Profitability Statement

| Particular | Actual FY 2024-25 | ABP FY 2025-26 | Likely FY 2025-26 | ABP FY 2026-27 |
| --- | --- | --- | --- | --- |
| Revenue : Solar / Coal Sale | 0.31 | 0.30 | 0.32 | 0.30 |
| EPC Revenue | — | — | — | 1,018.00 |
| SEZ Revenue (Rent + Development) | — | — | — | 59.46 |
| Brand Revenue (post AVPL merger) | — | — | — | 429.73 |
| EPTCL Stage 1 Arrear | — | 188.05 | — | 188.05 |
| Coal Trading | — | — | 37.29 | 400.00 |
| Interest Income on ICD | 192.00 | 150.14 | 113.60 | 113.57 |
| Other (Tax on Sale of Electricity / Refund) |  | 189 | 190 | — |
| Total Revenue | 193 | 527 | 341 | 2,209 |
| Total Expenses | 26 | 20 | 51 | 1,318 |
| EBITDA | 167 | 508 | 290 | 891 |
| Depreciation | 0.13 | 0.13 | 0.10 | 0.13 |
| Finance Expenses (NCD @ 20.5%) | 189 | 178 | 181 | 156 |
| PBT (before exceptional items) | (22) | 330 | 108 | 735 |
| Exceptional Items | 448 | 11 | — | 11 |
| Profit Before Tax | 426 | 341 | 108 | 746 |

EPOL ABP p.13.

Standalone Cash Flow Statement (FY 2026-27)

| Sources / Utilisation (INR Cr) | Q1 | Q2 | Q3 | Q4 | Total |
| --- | --- | --- | --- | --- | --- |
| Opening Balance | 2 | 7 | 115 | 102 | 2 |
| Total Inflow from Operations | 917 | 247 | 555 | 676 | 2,395 |
| Other Inflows (GUVNL, EPGL OCD) | 51 | — | — | 1,050 | 1,101 |
| Total Inflows | 967 | 247 | 555 | 1,726 | 3,496 |
| Total Utilisation | 962 | 139 | 568 | 1,685 | 3,354 |
| Closing Balance | 8 | 116 | 103 | 144 | 144 |

EPOL ABP p.15.

ESSAR POWER GUJARAT LIMITED (EPGL)

1. Key Developments

| # | Area | Detail | Reference |
| --- | --- | --- | --- |
| 1 | SHR, SOC & SWC Outperformance | Station Heat Rate achieved at 2,380 kcal/kWh (target: 2,383); Specific Oil Consumption at 0.15 ml/kWh (target: 0.25); Specific Water Consumption at 2.15 ML/MU (target: 2.25) : all metrics beat ABP targets. | EPGL ABP, Pg 13 |
| 2 | Higher UI / IEX Income | Unscheduled Interchange income of Rs.35 Cr vs. ABP target of Rs.12 Cr (~3x), driven by efficient real-time generation management by the operations team. | EPGL ABP, Pg 12:13 |
| 3 | PFC Disbursement Secured for SWIS | Rs.100 Cr disbursed in Dec’25 for the Sea Water Intake System project. EPC contract awarded to ECIL; mobilisation commenced. Rs.51 Cr capex paid and Rs.18 Cr LC issued for pipe supply. | EPGL ABP, Pg 19; Action Tracker #3 |
| 4 | Water Cost Savings | FY26 water cost likely at Rs.85 Cr vs. ABP target of Rs.101 Cr, a saving of Rs.16 Cr through efficient consumption management. | EPGL ABP, Pg 13 |
| 5 | FGD Exemption Secured | Under the revised government notification, EPGL falls under Category C : FGD installation is no longer mandatory. This avoids significant capex and higher auxiliary power consumption. | EPGL ABP, Pg 16 |

2. Areas of Concern

| # | Area | Detail | Reference |
| --- | --- | --- | --- |
| 1 | Grid Code Implementation Delayed | GERC has not amended the State Grid Code per CERC Amendment. The bench demitted office before listing; a new bench has been appointed. Annual EBITDA at risk: Rs.60 Cr. Claim of Rs.108 Cr filed; hearing likely April 2026. | EPGL ABP, Pg 9, 21:25 |
| 2 | Working Capital Facility : Not Yet Operational | Kotak Bank sanctioned Bill Discounting only in Mar’26 (planned Q3 FY26). Rs.1,000 Cr LC facility still under discussion, assumed from Jan 2027 only. Rebate on energy charge impacted. | EPGL ABP, Pg 8, 13; |
| 3 | Fly Ash Revenue Shortfall | FY26 likely fly ash sales at Rs.23 Cr vs. ABP target of Rs.34 Cr due to low demand and pricing. FY27 ABP targets Rs.1,503/MT via a proposed long-term contract : execution risk remains high. | EPGL ABP, Pg 13:14 |
| 4 | Finance Cost Escalation | Interest on unpaid coal creditors jumps from Rs.5 Cr (FY26 ABP) to Rs.54 Cr (FY27 ABP). Total finance cost budgeted at Rs.205 Cr for FY27 vs. Rs.130 Cr FY26 likely - a 58% increase, materially impacting profitability. | EPGL ABP, Pg 44 |
| 5 | Significant Litigation Exposure | Key pending matters: (a) GUVNL LD claim: Rs.180 Cr + Rs.299 Cr interest (Supreme Court); (b) Salaya-2 LD : Rs.80 Cr + Rs.244 Cr interest (GERC); (c) LTOA Relinquishment : Rs.555 Cr (APTEL); (d) GUVNL Coal Cost counter-claim : Rs.205 Cr (GERC). | EPGL ABP, Pg 38:41 |
| 6 | EBITDA-to-PAT Conversion Gap | Despite projected EBITDA of Rs.260 Cr (45% margin), EPGL budgets a net loss of Rs.58 Cr for FY27. High finance costs (Rs.205 Cr) and depreciation (Rs.116 Cr) consume operating profits. Cash PBT is only Rs.55 Cr. | EPGL ABP, Pg 43 |

3. Recommended Focus Area for Discussion

| # | Area | Detail | Reference |
| --- | --- | --- | --- |
| 1 | SWIS Commissioning : Timeline & Cost Assurance | Annual savings of Rs.86 Cr hinge on commissioning by Nov’26. Management to confirm whether construction milestones are on track and if Rs.205 Cr project cost envelope holds. | EPGL ABP, Pg 8, 19; |
| 2 | Grid Code : Escalation Strategy | FY27 ABP assumes Rs.60 Cr SHR compensation, but petition is yet to be listed at GERC. Retrospective claim for FY24-25 alone is Rs.109 Cr. Timeline and escalation plan should be established. | EPGL ABP, Pg 9, 24:25; Action Tracker #2 |
| 3 | Finance Cost & Coverage Ratios | Finance cost rising from Rs.130 Cr to Rs.205 Cr needs scrutiny. DSCR at 0.50x and Interest Coverage at 0.70x remain below 1.0x : improvement path to be clarified. | EPGL ABP, Pg 15, 43:44 |
| 4 | Fly Ash : Achievability of Rs.57 Cr Target | FY27 target is ~2.5x FY26 likely (Rs.23 Cr). Assumes Rs.1,503/MT pricing and 100% ash utilisation. | EPGL ABP, Pg 14, 18 |
| 5 | GUVNL Holdback & Coal Cost Dispute | Holdback amount of Rs.136 Cr subject to GERC order. GUVNL counter-claims Rs.205 Cr (alleged excess Russian coal payments); EPGL counter-claims Rs.125 Cr. Resolution timeline and litigation strategy to be discussed. | EPGL ABP, Pg 8:9, 40 |
| 6 | Credit Rating Upgrade Roadmap | Target: upgrade to “A” post SWIS, WC tie-up, and DSRA creation. Requires steady-state EBITDA of Rs.450 Cr (vs. current ~Rs.240 Cr) and DSCR >1.75x. Management to present the rating agency engagement plan and timeline. | EPGL ABP, Pg 15, 33 |

4. Financial Summary

4.1 Profitability Summary

| Particulars (Rs. Cr) | FY25 Actual | FY26 Est. |  |  | FY27 ABP |
| --- | --- | --- | --- | --- | --- |
| Total Revenue | 418 | 520 |  |  | 575 |
| Coal Under Recovery | (136) | (44) |  |  | (25) |
| Net Capacity Charges | 511 | 520 |  |  | 528 |
| Other Income | 43 | 44 |  |  | 71 |
| EBITDA (Adj.) | 125 | 220 |  |  | 260 |
| EBITDA Margin (%) | 30% | 42% |  |  | 45% |
| Finance Cost | 174 | 130 |  |  | 205 |
| Depreciation | 111 | 112 |  |  | 116 |
| PBT | (119) | (18) |  |  | (58) |
| Cash PBT | (48) |  | 90 | 55 |  |

Source: EPGL ABP, Pg 43:45

4.2 Key Balance Sheet & Coverage Metrics

| Metric | FY26 Est. | FY27 Target | Remarks |
| --- | --- | --- | --- |
| Capex | Rs.124 Cr | Rs.114 Cr | Primarily SWIS |
| Debt Raise | Rs.100 Cr | Rs.502 Cr |  |
| Debt / Equity | 0.96x | 0.60x |  |
| DSCR | 0.60x | 0.50x |  |
| Interest Coverage | 0.85x | 0.72x |  |
| Current Ratio | 0.89x | 1.74x | Improved with WC facility |
| FCFF | : | Rs.226 Cr |  |

Source: EPGL ABP, Pg 32, 48

4.3 EBITDA Bridge: FY26 Likely → FY27 ABP

| Parameter | Impact (Rs. Cr) |
| --- | --- |
| FY26 Likely EBITDA (Base) | 220 |
| Lower Coal Under Recovery (Forex / IEX / SHR Comp.) | +20 |
| Net Capacity Charge (Higher per PPA) | +8 |
| Fly Ash : Sale Price Improvement | +34 |
| Water Cost Reduction (post SWIS) | +10 |
| Other Income (One-time FY26 writeback removed) | (7) |
| Employee Cost Increase | (15) |
| Secondary Fuel & O&M / SGA | (10) |
| FY27 ABP EBITDA | 260 |

Source: EPGL ABP, Pg 15

5. Action Tracker Summary (Open Points as on 10.03.2026)

21 open action items across categories. Key items summarised below:

| # | Action Item | Timeline | Status | Latest Update |
| --- | --- | --- | --- | --- |
| 1 | GUVNL invoice approval / coal cost petition | Jun’25 | Delayed | Petition awaiting listing at GERC (likely April 2026). GUVNL currently paying 100% as per invoices. |
| 2 | Grid Code benefits : retrospective claim | Jun’25 | Delayed | Petition filed; GERC bench reconstituted. Matter likely listed April 2026. |
| 3 | PFC funding for SWIS | With ABP | On Track | Rs.100 Cr disbursed (Dec’25). Rs.51 Cr capex paid; Rs.18 Cr LC issued for pipes. |
| 4 | Kotak WC facility / LC tie-up | Mar’26 | On Track | Bill Discounting sanctioned; T&C modification requested. Rs.1,000 Cr LC under discussion. |
| 5 | GUVNL holdback recovery | Jun’25 | On Track | Rs.65 Cr released; balance amt. subject to GERC coal cost order. |
| 8 | Hedging implementation | Apr’25 | Delayed | Linked to Kotak facility. Now being pursued via Kotak structure. |
| 12 | Conventional power strategic plan | Feb’26 | On Track | 3:4 GW target by 2030: 1.2 GW operational, 1.6 GW brownfield Salaya, 1 GW gas UK. |
| 14 | GUVNL tender participation | Feb’26 | Open | GUVNL finalising tender docs. EPGL represented to GoG on RSR transport and BTG conditions. |
| 16 | Achieve Rs.400:450 Cr EBITDA | Jul’26 | On Track | Current ~Rs.240 Cr. Pathway: SWIS (~Rs.100 Cr), Grid Code (~Rs.60 Cr), Incentive for higher plant availability (~Rs.15 Cr), O&M cost reduction (~Rs.20 Cr). |
| 18 | Release of Rs.136 Cr holdback | Jun’26 | On Track | Balance release subject to GERC order. New bench appointed; hearing likely April 2026. |

Source: EPGL Action Tracker Report (Open Points, 10.03.2026)

Essar Renewables Limited (ERL)

1. Key Developments

| # | Area | Detail | References |
| --- | --- | --- | --- |
| 1 | RE Zone Declaration & Connectivity Wins | ERL successfully engaged with MNRE, MoP, CEA, CTUIL, and industry bodies (NSEFI, WIPPA, SPDA) to secure the RE Zone declaration for Tumkur-II and expand substation capacity from 1.5 GW to 4.2 GW. Connectivity for NHPC solar and FDRE on time. | ERL ABP, p.22, 29 |
| 2 | Project Finance Documentation (SJVN) | IREDA sanctioned Rs 975.25 Cr RTL and Rs 70.65 Cr PBG facility for the SJVN 300 MW Solar project. Facility documentation was completed within 6 months of sanction, meeting the timeline. | ERL ABP, p.27 |
| 3 | New Lender Onboarding (Bank of Maharashtra) | Bank of Maharashtra sanctioned Rs 200 Cr RTL and Rs 70.65 Cr PBG participation in the IREDA facility, enabling early PBG release (80% margin on PPA signing) without waiting for IREDA PDCs. This diversifies the lender base for the RE portfolio. | ERL ABP, p.22, 27 |
| 4 | 4 GW Strategic Roadmap Finalized | ERL finalized a clear Anchor-Build-Expand (A-B-E) strategy: 3 GW domestic (utility + captive) and 1 GW international (Indonesia). The strategy aligns with GMC’s 10 GW power suggestion (of which ~6 GW RE) and has been reflected in the FY27 ABP. | ERL ABP, p.4; GMC MoM, p.2:3 |
| 5 | Indonesia Market Entry Progress | PT AMI successfully submitted the Expression of Interest and Pre-Qualification for 1.1 GW PLN Nusantara Power tenders. Stage-1 covers 200 MW across four sites (Paiton, Batang, Sumenep-1, Pemalang) with CODs in 2027:28. | ERL ABP, p.8 |

2. Areas of Concern

| # | Area | Detail | References |
| --- | --- | --- | --- |
| 1 | Delays in Land Acquisition | Land acquisition for SJVN, NHPC, and NHPC FDRE projects was a “Miss” in FY26 due to funding delays, late GO applications, and rising competition. Land lease rates have escalated (landowners demanding 2:5 years’ upfront rent), and high-CUF sites are being lost to competitors. | ERL ABP, p.22:23 |
| 2 | PPA Signing Delays Across All Three Projects | PPAs for the entire 900 MW (SJVN Solar, NHPC Solar, NHPC FDRE) remain unsigned. Approval to pursue PPAs came only in H2 CY25, by which time CTUIL evacuation delays created further bottlenecks. A single DISCOM is now being considered for all 900 MW offtake. | ERL ABP, p.22, 29 |
| 3 | IREDA Disbursement Timeline Breach (SJVN) | The IREDA disbursement deadline of 8th March 2026 has been breached due to PPA delay. Extension request has been submitted but not yet approved. Worst case: IREDA re-appraises the project, risking terms and timeline. | ERL ABP, p.27 |
| 4 | Significant Funding Shortfall & Equity Gap | Against a Rs 378 Cr investment plan till FY26, only Rs 93 Cr was invested by Feb 2026. FY27 requires Rs 1,362 Cr total (Rs 611 Cr Essar contribution). JV/Mezz partner discussions for equity closure are still ongoing. | ERL ABP, p.18, 25:26 |
| 5 | SJVN Connectivity Delay (Tumkur-II) | The Tumkur-II ISTS transmission scheme timeline has been revised from 24 months to 36 months under TBCB, potentially pushing SJVN connectivity to June 2029. ERL is engaging MoP and CEA for phased implementation targeting June 2028. | ERL ABP, p.29 |
| 6 | Manpower Retention | Slow project progress and lack of tender participation have made manpower retention difficult. | ERL ABP, p.23 |

3. Recommended Focus Areas for Discussion

| # | Area | Detail | References |
| --- | --- | --- | --- |
| 1 | PPA Execution Certainty & DISCOM Diversification | Management should confirm: (a) contingency if the single DISCOM does not absorb all 900 MW, and (b) whether alternate DISCOMs (MP, UP, Bihar, Chhattisgarh, Punjab) remain viable fallback options. | ERL ABP, p.29 |
| 2 | Equity & JV Partner Closure (CIP) | CIP discussions for equity closure (SHA/SSA/EPC reported as “close to finalization”) have been ongoing since Aug 2025. A timeline for financial close and clarification of Essar’s exposure if JV/Mezz partner does not materialize by Q2 FY27 should be discussed. | Action Tracker Point 6, 7; ERL ABP, p.25; GMC MoM, p.2 |
| 3 | IRR vs. GMC Hurdle Rate Gap | ABP projects show Equity IRRs of 13:17%, while the GMC has set a 30% all-inclusive Equity IRR hurdle. | ERL ABP, p.17; GMC MoM, p.2 |
| 4 | FY27 Capex Execution Readiness | Rs 1,199 Cr of project capex is planned for FY27 across three existing projects, heavily back-loaded (Rs 438 Cr in Q4 alone; Rs 290 Cr in Q4 for NHPC FDRE). Procurement pipelines, EPC readiness and if fund flows can support this profile, should be looked at. | ERL ABP, p.26 |
| 5 | Bidding Pipeline Funding (Rs 485 Cr) | The ABP identifies Rs 485 Cr required for future bidding costs (EMD/PBG for Punjab, Rajasthan, Karnataka + Rajasthan land at Rs 315 Cr + Gujarat land at Rs 27 Cr). The source and approval status for this capital, should be looked at, given the existing equity constraints. | ERL ABP, p.28 |

4. Summary of Financials

4.1 Existing Projects : Key Financial Parameters

| Particulars (Rs Cr) | SJVN Solar | NHPC Solar | NHPC FDRE |
| --- | --- | --- | --- |
| Project Overview |  |  |  |
| Capacity | 300 MWac | 300 MWac | 300 MWac |
| Location | Tumkur, KA | Kurnool, AP | Kurnool/Anantapur, AP |
| Expected Completion | Mar 2028 | Mar 2028 | Feb:Mar 2028 |
| Project Cost & Financing |  |  |  |
| Total Project Cost | 1,301 | 1,337 | 4,528 |
| Debt (75%) | 976 | 1,003 | 3,396 |
| Equity (25%) | 325 | 334 | 1,132 |
| Interest Rate | 9.5% | 9.5% | 9.5% |
| Investment Status (as of Feb 2026) |  |  |  |
| Total Invested Till FY26 | 163 | 105 | 110 |
| of which Project Capex | 62 | 15 | 83 |
| of which BG (net of releases) | 100 | 90 | 28 |
| FY27 Requirement |  |  |  |
| Project Capex Required FY27 | 229 | 167 | 803 |
| Net BG Movement FY27 | (62) | (62) | 49 |
| Total FY27 Investment | 167 | 105 | 851 |
| Returns & Sensitivity |  |  |  |
| Tariff (Rs/kWh) | 2.56 | 2.56 | 4.37 |
| Projected Equity IRR | 16.02% | 15.58% | 16.15% |
| CUF Sensitivity (1% drop → IRR impact) | :0.49% | :0.48% | :0.56% |
| Capex Sensitivity (5% rise → IRR impact) | :2.29% | :2.27% | :2.39% |
| Interest Rate Sensitivity (1% rise → IRR) | :2.49% | :2.50% | :2.73% |

Source: ERL ABP p. 3, 17, 18, 21

4.2 Proposed Utility-Scale (STU) Projects FY27

| Proposed Projects (Rs Cr) | Punjab 50 MW | Rajasthan 250 MW | Karnataka 200 MW |
| --- | --- | --- | --- |
| Asset Type | Solar | Solar + BESS | Solar + BESS |
| Total Budget | 223 | 2,254 | 1,803 |
| BG Requirement (EMD + PBG) | 17 | 104 | 100 |
| Target IRR | ~16:17% | ~16:17% | ~16:17% |

Source: EPL ABP p. 3

4.3 Consolidated Funding Requirement : FY27

| Consolidated FY27 Funding (Rs Cr) | Existing | Additional | Total |
| --- | --- | --- | --- |
| Project Capex | 1,199 | 208 | 1,407 |
| Net BG Movement | (75) | 30 | (45) |
| Total Funding Requirement | 1,124 | 238 | 1,362 |
| Essar’s Contribution (FY27) |  |  | 611 |

Source: ERL ABP, p. 25:26

5. GMC Action Tracker : RE Open Points (as of March 2026)

| # | Category | Action Item | Status | Latest Update |
| --- | --- | --- | --- | --- |
| Approvals |  |  |  |  |
| 1 | Wheeling Policy | Negotiate with state govts for better wheeling & banking policies for RE projects | On Track | Tentative projections received for BEM; added in ABP. Discussions with state depts to begin Q3 FY27. |
| 2 | Land Approvals | Get all land-related approvals (GO, connectivity, RE zone) | Delayed | ERSOL: GO initiated by KREDL; RE zone declared; connectivity agreed at 42nd CMETS : in-principle grant awaited. ERSTL/ERHOL: GO applied at NREDCAP; processing fee pending. |
| PPAs |  |  |  |  |
| 3 | PPA Signing | Sign PPAs and PSAs in a sequenced manner (Dec’25:May’26) | On Track | DISCOM expected to confirm REIA by 31st March. REIA consent by 4th April. Solar PPAs expected Apr’26; FDRE PPA expected May’26. |
| 4 | PPA Cash Plan | Draw up cash requirements to ensure PPAs are signed in sequence | On Track | PBG submission planned Apr’26:May’26. |
| Fund Raise & Bank Guarantees |  |  |  |  |
| 5 | BG : SJVN/FDRE | Secure bank guarantees for SJVN and NHPC FDRE projects | On Track | BoM final sanction received (PBG + RTL Rs 200 Cr). 80% PBG margin release on PPA signing. Documentation on hold pending PPA clarity. FDRE BG discussions ongoing. |
| 6 | Equity Raise | Sign funding term sheets; raise capital for existing RE projects | On Track | FDRE: CIP discussions ongoing; SHA/SSA/EPC close to finalization. ERHOL cleared CIP IC1 (conditional). Solar: ERSOL/ERSTL proposal pending CIP approval. |
| 7 | Strategic Investor | Bring in strategic/PE investor for 51:74% stake in ERL assets | On Track | Discussions with CIP ongoing for equity closure. |
| Strategy & Planning |  |  |  |  |
| 8 | RE Strategy | Finalize the renewables power strategic plan | Closed | Strategy plan including 4 GW RE finalized. |
| 9 | EPC Margin Model | Include EPC margin benefits in RE model as separate case | On Track | To be done during individual bid approval process. Timeline: May’26. |
| 10 | FY27 ABP | Finalize FY27 ABP based on strategy | Closed | ABP circulated. |
| Indonesia Project |  |  |  |  |
| 11 | PLN Enrolment | Finalize structure and complete enrolment with PLN Indonesia | On Track | Ongoing. |
| 12 | Project Analysis | Complete detailed analysis with project report and recommendations | On Track | EOI submitted to PLN. PQ resubmission by PT AMI due Apr’26. |
| Land |  |  |  |  |
| 13 | Solar Park Land | Finalize land for solar park initiative (Maharashtra / Ladakh) | On Hold | On Hold: Change in Ladakh administration; unfavorable rates from Maharashtra. |
| 14 | NHPC Land | Sign term sheets with land aggregators for NHPC projects | On Track | Ongoing. Awaiting GO boundary confirmation. |